## Change log
Change request log template
Free template from Critova · critova.com · project management and project controls software
CR ID | Change | Requested by | Date | Reason | Cost impact | Schedule impact (days) | Decision | Decision date | Decided by
CR-01 | Add a second loading bay | Operations | 2026-09-20 | Forecast volumes increased. | 45000 | 10 | Approved | 2026-09-28 | Sponsor
CR-02 | Upgrade lobby finishes | Client | 2026-10-01 | Brand standards. | 18000 | 0 | Pending
Approved cost change
Approved schedule change (days)

## How to use this template
Change request log template
Record every requested change with its reason and its impact on cost and schedule, then the decision. The totals at the bottom show how much approved change the project has absorbed.
Column | What to enter
Free template from Critova · critova.com · project management and project controls software