## EVM tracker
Earned value tracker template
Free template from Critova · critova.com · project management and project controls software
Budget at completion (BAC) | 1000000
Period | PV (cumulative) | EV (cumulative) | AC (cumulative) | CPI | SPI | CV | SV | EAC (BAC / CPI)
Month 1 | 100000 | 90000 | 95000
Month 2 | 220000 | 200000 | 215000
Month 3 | 360000 | 300000 | 330000
Month 4 | 400000 | 350000 | 420000

## How to use this template
Earned value tracker template
Enter the budget once, then the cumulative planned value, earned value and actual cost each month. Every row shows CPI, SPI, the variances and the forecast cost at completion.
Column | What to enter
Free template from Critova · critova.com · project management and project controls software