## Issue log
Issue log template
Free template from Critova · critova.com · project management and project controls software
ID | Issue | Date raised | Raised by | Owner | Priority | Action | Due date | Status | Date closed | Days open
I-01 | Concrete test results for level 3 failed; slab must be re-tested. | 2026-10-02 | Site engineer | Quality manager | High | Core samples and engineer review. | 2026-10-09 | In progress
I-02 | Client has not approved the finishes sample board. | 2026-09-25 | Project manager | Design manager | Medium | Escalate at the steering committee. | 2026-10-06 | Open
Formulas:
Days open = IF([Date raised]="","",IF([Date closed]<>"",[Date closed]-[Date raised],TODAY()-[Date raised]))

## How to use this template
Issue log template
An issue log for problems that have already happened. Each issue gets an owner, a priority and an action, and the sheet counts how many days it has been open.
Column | What to enter
Free template from Critova · critova.com · project management and project controls software