## Lessons
Lessons learned template
Free template from Critova · critova.com · project management and project controls software
ID | Phase | What happened | Effect | Repeat or change | Recommendation | Owner
L-01 | Planning | Long-lead items were ordered after design freeze. | Six weeks of float lost on the critical path. | Change | Order long-lead items at 60% design with a cancellation clause. | Procurement lead
L-02 | Execution | Weekly look-ahead meetings with subcontractors. | Fewer clashes between trades. | Repeat | Make the look-ahead part of the standard project setup. | Planning manager

## How to use this template
Lessons learned template
Capture lessons as they happen, not only at the end. Each row records what happened, what it caused, and a recommendation with an owner, so the next project can act on it.
Column | What to enter
Free template from Critova · critova.com · project management and project controls software