## Charter
Project charter template
Free template from Critova · critova.com · project management and project controls software
Section | Content | What good looks like
Project name | Warehouse expansion, phase 2 | Short and unique.
Sponsor | Operations director | One named person who owns the business case.
Project manager | (name) | The person accountable for delivery.
Purpose | Add 4,000 m² of storage to meet forecast demand. | Why the project exists, in one or two sentences.
Objectives | Handover by 31 March 2027; within $2.4M; zero lost-time injuries. | Measurable: date, money, quality.
In scope | Building, racking, fire systems, two loading bays. | What will be delivered.
Out of scope | Warehouse management software; fleet changes. | What people might assume but is not included.
Key milestones | Design freeze Nov 2026; steel complete Jan 2027; handover Mar 2027. | Four to eight dates the sponsor cares about.
Budget | $2.4M including 10% contingency. | State what reserves are included.
Main risks | Long-lead switchgear; permit timing. | The three to five that could change the plan.
Stakeholders | Operations, finance, facilities, local authority. | Who must be consulted or informed.
Approval | Sponsor signature and date | Without a signature it is a draft.

## How to use this template
Project charter template
A one-page charter that authorises the project. Each field has a prompt that tells you what a good answer looks like; replace the example text with yours and get it signed.
Column | What to enter
Free template from Critova · critova.com · project management and project controls software