## Risk register
Risk register template
Free template from Critova · critova.com · project management and project controls software
ID | Risk (cause, event, effect) | Owner | Probability (1-5) | Impact (1-5) | Score | Rating | Probability % | Cost if it happens | EMV | Delay if it happens (days) | Response | Response actions | Due date | Status
R-01 | Because the supplier has a long order book, switchgear may arrive late, delaying energisation. | Procurement lead | 4 | 4 |  |  | 30% | 200000 |  | 20 | Mitigate | Pre-qualify a second supplier; order by week 6. | 2026-11-15 | In progress
R-02 | Because permits depend on a third party, approval may take longer than planned, delaying site start. | Project manager | 3 | 4 |  |  | 25% | 80000 |  | 15 | Mitigate | Submit early; weekly follow-up meeting. | 2026-10-30 | Open
R-03 | Because two key engineers share projects, availability may drop in peak weeks, slowing design. | Design manager | 2 | 3 |  |  | 15% | 30000 |  | 8 | Accept | Agree priority dates with the PMO. | 2026-11-01 | Open

## How to use this template
Risk register template
A ready-to-use risk register. Score each risk 1 to 5 for probability and impact and the sheet calculates the score, the rating band and the expected monetary value for you.
Column | What to enter
Risk (cause, event, effect) | Because of X, Y may happen, which would lead to Z.
Owner | One named person.
Score | Probability × impact.
Rating | 15-25 high, 6-14 medium, 1-5 low.
EMV | Probability % × cost.
Free template from Critova · critova.com · project management and project controls software