## Status
Project status report template
Free template from Critova · critova.com · project management and project controls software
Area | Status | Trend | Comment and next action
Overall | Amber | Stable | On track for handover; supplier risk being managed.
Schedule | Amber | Worsening | Switchgear delivery 2 weeks late; mitigation in place.
Cost | Green | Stable | CPI 1.02; within budget.
Scope | Green | Stable | No open change requests.
Risks | Amber | Stable | 2 high risks; both have owners and actions.
Resources | Green | Stable | Team fully staffed.

## Milestones
Project status report template
Free template from Critova · critova.com · project management and project controls software
Milestone | Baseline date | Forecast date | Slip (days) | Status
Design complete | 2026-10-15 | 2026-10-15 |  | Green
Switchgear delivered | 2026-11-20 | 2026-12-04 |  | Amber
Practical completion | 2027-03-31 | 2027-04-07 |  | Amber

## How to use this template
Project status report template
A one-page status report: a red, amber or green status for each area with a short comment, and a milestone table that compares forecast dates with the baseline.
Column | What to enter
Free template from Critova · critova.com · project management and project controls software